## Slide 1: Office Queue Management
Team 6
Sprint Retrospective

## Slide 2: Review
Sprint:
Following stories implemented:
  booking tickets by the customers
  calling a ticket to be served in a specific counter by Officer
  Notifying the customers once they are called to the counter
  configuring the counters
Feedback:
  Positive: Suitable User Interface
  Negative: Text on the Buttons are small

## Slide 3: Process
Number of stories committed/done: 4/3
Total points committed/done: 15/10
Number of hours planned/spent: 36/49
Hours per task: 5.4 (avg),
Total task estimation error ratio: 0.73
ID story | # Tasks | Points | Hrs estimated | Hrs Spent
OQ-1 | 3 | 5 | 11 | 14
OQ-2 | 2 | 3 | 8 | 13.5
OQ-6 | 2 | 2 | 10 | 5
OQ-17 | 2 | 5 | 7 | 16.5

## Slide 4: Testing
We included our estimation of testing in the task estimation, so we don’t have time tracked only for testing.
Total hours spent: 1hrs

## Slide 5: Assessment
Some planned stories have not been done so far because of the evaluation issue. Some tasks required more time to complete.
The estimation errors mostly stemmed from the lack of experience in workload assessment and the adoption of new technologies.
The way of communication with each other and the importance of time management is the most critical point assimilating by team members.

## Slide 6: Assessment
Taking the benefit of operating on different Branches instead of just working on the Master branch to manage the project better is the one that will enhance in the next sprint.
We are proud of finishing our first sprint with a working product.