## Slide 1: Office Queue
Team 6 Sprint Retrospective

## Slide 2: Review
Sprint:
  We implemented the stories about booking a ticket, calling a ticket to a counter to be served, notifyink a customer when he is called to a counter and configuring the counters.
Feedback:
  Positive: Nice user interface
  Negative: Small text in buttons

## Slide 3: Process
Number of stories committed/done: 4/3
Total points committed/done: 15/10
Number of hours planned/spent: 36/49
Hours per task: 5.4 (avg),
Total task estimation error ratio: 0.73
ID story | # Tasks | Points | Hrs extimaded | Hrs spent
OQ-1 | 3 | 5 | 11 | 14
OQ-2 | 2 | 3 | 8 | 13.5
OQ-6 | 2 | 2 | 10 | 5
OQ-17 | 2 | 5 | 7 | 16.5

## Slide 4: Testing
We included our estimation of testing in the task estimation, so we don’t have time tracked only for testing.
Total hours spent: 1

## Slide 5: Assessment
We did not complete all planned stories, because we under-evaluetad some tasks that required more time.
Our errors in estimation were caused by inexperience in estimating the workload and the use of new technologies.
We learn the importance of communication and time management.
We should take advanteg of the branches provided by GIT.
We are proud of finishing our first sprint with a working product.